## Slide 1
humagen / Spring Launch
INTERNAL LAUNCH BRIEFING
A controlled shift to November 19.
Protect the retail launch buffer. Keep the November 12 press embargo.
INTERNAL DRAFT / SAMPLE DATA / LEADERSHIP
1 / 6
Notes: This is an internal draft for review. The recommendation does not authorize changing dates or sending external notices.

## Slide 2
humagen / Spring Launch
THE SEQUENCE
Three dates. One clear sequence.
Packaging arrives before the press embargo and retail availability.
Nov 8
Packaging arrives
Nov 12
Press embargo
Nov 19
Retail availability
INTERNAL DRAFT / SAMPLE DATA / LEADERSHIP
2 / 6
Notes: Packaging moved from November 4 to November 8. The extra week protects fulfilment. The press announcement should state the retail availability date clearly.

## Slide 3
humagen / Spring Launch
IMPACT
What changes, what holds.
Keep the recommendation separate from actions that still need approval.
• Retail availability moves seven days to November 19.
• The press embargo remains November 12.
• Paid media requires its own review after source access is restored.
INTERNAL DRAFT / SAMPLE DATA / LEADERSHIP
3 / 6
Notes: The media buy tracker was excluded from this recommendation because its access expired. The dates use the permitted supplier ETA, retail calendar, and plan snapshot.

## Slide 4
humagen / Spring Launch
DECISIONS
Two approvals. Two boundaries.
A date decision never silently authorizes external delivery.
• Jamie Davis approves or redirects the proposed retail date.
• Four vendor notices are reviewed separately before sending.
• Ops holds delivery until that specific action is approved.
INTERNAL DRAFT / SAMPLE DATA / LEADERSHIP
4 / 6
Notes: These are proposed actions in a sample design. No notices were sent. Each approval should identify its actor, target, and exact content or change.

## Slide 5
humagen / Spring Launch
OWNERSHIP
The next step has an owner.
Keep progress visible without asking people to supervise every tool call.
• Launch Planner maintains the plan and completion criteria.
• Ops prepares vendor notices and holds delivery.
• Jon T. restores and verifies access to the media source.
INTERNAL DRAFT / SAMPLE DATA / LEADERSHIP
5 / 6
Notes: A question about presentation audience blocks only the briefing assignment. Date approval, source restoration, and message approval remain separate work.

## Slide 6
humagen / Spring Launch
EVIDENCE AND FOLLOW-THROUGH
Grounded, versioned, and ready to review.
Every output points back to the work and the evidence that produced it.
• Supplier ETA: indexed October 23 at 09:42 UTC.
• Retail calendar: live search as Jamie at 09:47 UTC.
• Launch plan v3: snapshot imported October 18.
INTERNAL DRAFT / SAMPLE DATA / LEADERSHIP
6 / 6
Notes: This briefing is version 1, a draft. Review the outcome, request slide-specific changes, and retain prior versions when new outputs are produced.