# Launch plan

Version 4 · Spring Launch · Internal draft · Sample data

# Recommendation

Move retail availability to November 19. Keep the press embargo on November 12.

# Why

Packaging now arrives November 8, four days later than planned. The revised retail date restores the fulfilment buffer.

# Milestones

November 8: packaging arrives. November 12: press embargo. November 19: retail availability.

# Approvals

Jamie Davis reviews the date. Four vendor notices require a separate delivery approval.

# Owners

Launch Planner owns the plan. Ops prepares notices. Jon T. restores access to the media buy tracker.

# Evidence

Supplier ETA indexed October 23, 09:42 UTC. Retail calendar queried as Jamie at 09:47 UTC. Launch plan v3 imported October 18.

# Status

Internal draft for review. No external messages have been sent from this sample.